## Worksheet
Project Timeline - Process Documentation
Phase | Activity | Start Date | End Date | Status | Responsible Team/Person
Initiation Phase | Project Charter Development | 2024-01-05 | 2024-01-15 | In Progress | Project Manager, Team Lead A
| Stakeholder Identification & Analysis | 2024-01-16 | 2024-01-25 | In Progress | Business Analyst, Team Lead B
| Risk Assessment & Mitigation Planning | 2024-01-26 | 2024-01-31 | Pending | Risk Manager, Team Lead C
Design Phase | Requirements Gathering & Documentation | 2024-02-01 | 2024-02-15 | In Progress | Business Analyst, Team Lead D
| User Interface Mockups & Prototypes | 2024-02-16 | 2024-03-15 | Pending | UI/UX Designer, Team Lead E
| System Architecture Design | 2024-03-16 | 2024-03-31 | Pending | Lead Architect, Team Lead F
| Technical Design Review & Approval | 2024-04-01 | 2024-04-15 | Pending | CTO, Technical Committee
Development Phase | Core Module Development (Phase 1) | 2024-04-16 | 2024-05-31 | Pending | Development Team, Tech Lead G
| API Development & Integration Testing | 2024-06-01 | 2024-06-30 | Pending | Backend Team, DevOps Lead H
| Frontend Development & UI Implementation | 2024-07-01 | 2024-08-15 | Pending | Frontend Team, Dev Lead I
| Unit & Integration Testing (Phase 1) | 2024-08-16 | 2024-09-30 | Pending | QA Team, QA Lead J
| Code Refactoring & Optimization | 2024-10-01 | 2024-10-31 | Pending | Senior Developers, Tech Lead K
Testing Phase | System Integration Testing (SIT) | 2024-11-01 | 2024-11-30 | Pending | QA Team, QA Lead J
| User Acceptance Testing (UAT) | 2024-12-01 | 2024-12-31 | Pending | End Users, Stakeholder Reps
| Bug Fixing & Regression Testing | 2025-01-01 | 2025-01-31 | Pending | Development & QA Teams, Tech Lead L
| Final Testing Sign-off & Approval | 2025-02-01 | 2025-02-14 | Pending | CIO, Steering Committee
Deployment Phase | Production Environment Setup | 2025-02-15 | 2025-03-14 | Pending | DevOps Team, Infra Lead M
| Staged Rollout (Phase 1) | 2025-03-15 | 2025-04-14 | Pending | Implementation Team, Deployment Lead N
| Full Production Rollout & Monitoring | 2025-04-15 | 2025-04-30 | Pending | All Teams, Project Manager O
Closure Phase | Post-Implementation Review & Documentation | 2025-05-01 | 2025-05-14 | Pending | Closure Lead, Project Manager O
| Knowledge Transfer & Training Sessions | 2025-05-15 | 2025-06-30 | Pending | Trainers, Support Team P
| Final Project Report & Handover to Operations | 2025-07-01 | 2025-07-31 | Pending | Project Manager, Operations Lead Q
Project Timeline - Process Documentation (Page 2)
Dependencies | Risks & Mitigations | Key Milestones | Budget Allocation (USD)
Project Charter Approval → Stakeholder Analysis Stakeholder Analysis → Risk Assessment | Unclear project scope – Mitigation: Conduct regular stakeholder alignment meetings Limited resources – Mitigation: Prioritize critical activities and adjust timelines | Project Charter Signed (Jan 15, 2024) Stakeholder Register Finalized (Jan 25, 2024) | $45,000
Requirements Finalization → UI Prototypes UI Prototypes → System Architecture System Architecture → Technical Review | Changing requirements – Mitigation: Implement change control process Design delays – Mitigation: Allocate buffer time and use agile sprints | Requirements Sign-off (Feb 15, 2024) UI Prototypes Approved (Mar 15, 2024) Architecture Approval (Mar 31, 2024) | $89,500
Design Approval → Core Module Development Core Modules → API Integration Integration Testing → Frontend Implementation | Technical debt accumulation – Mitigation: Code reviews and refactoring sprints Bottlenecks in testing – Mitigation: Expand QA resources during peak cycles | Phase 1 Development Complete (May 31, 2024) API Integration Completed (Jun 30, 2024) Frontend Implementation Complete (Aug 15, 2024) | $375,000
Development Complete → SIT SIT Complete → UAT UAT Feedback → Bug Fixing | Defects discovered late – Mitigation: Shift left testing and early validation User resistance to new system – Mitigation: Early training sessions and feedback loops | SIT Completion (Nov 30, 2024) UAT Sign-off (Dec 31, 2024) Final Testing Approval (Feb 14, 2025) | $68,000
Testing Approved → Environment Setup Environment Ready → Staged Rollout Staged Rollout Complete → Full Deployment | Production failure during rollout – Mitigation: Implement rollback plans and phased deployment Data migration issues – Mitigation: Test data in staging, validate integrity pre-deployment | Production Setup Complete (Mar 14, 2025) Staged Rollout Complete (Apr 14, 2025) Full Production Live (Apr 30, 2025) | $97,300
Production Launch → Post-Implementation Review Training Completion → Final Report Submission | Knowledge transfer gaps – Mitigation: Document all processes and conduct Q&A sessions Ongoing support issues – Mitigation: Establish helpdesk and monitoring systems | Post-Implementation Review Complete (May 14, 2025) Training Sessions Completed (Jun 30, 2025) Final Handover & Report Submitted (Jul 31, 2025) | $48,700
Notes:
All dates are estimated and subject to change based on actual progress.
Status values represent the current state: Pending, In Progress, Completed.
Resource allocation is monitored monthly for budget tracking.