## Worksheet
Project Timeline - Process Documentation
Phase | Task Description | Start Date | End Date | Responsible Team | Status
Initiation | Define project scope and objectives | 2024-01-05 | 2024-01-15 | Project Management Office | In Progress
Planning | Develop detailed project plan and timeline | 2024-01-16 | 2024-01-31 | Project Team Lead, PMO | Pending
Execution | Begin development and implementation activities | 2024-02-01 | 2024-03-31 | Development Team, QA Engineers | Pending
Testing & Validation | Conduct unit testing, system integration, and user acceptance testing | 2024-04-01 | 2024-05-15 | Quality Assurance Team | Pending
Closure | Final review, documentation, project sign-off, and handover | 2024-05-16 | 2024-06-15 | Project Manager, Stakeholders | Pending