## Worksheet
Project Timeline - Process Documentation
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
Initiation | Project Kickoff Meeting & Scope Definition | 2024-01-05 | 2024-01-15 | In Progress | Project Manager, Team Leads
Planning | Resource Allocation & Work Breakdown Structure (WBS) | 2024-01-16 | 2024-01-31 | To Do | Project Planner, PMO
Design & Development | System Architecture Design & Initial Prototyping | 2024-02-01 | 2024-03-15 | To Do | Development Team, UX/UI Designers
Implementation | Core Module Development & Integration Testing | 2024-03-16 | 2024-05-10 | To Do | Development Team, QA Engineers
Testing & Validation | User Acceptance Testing (UAT) & Bug Fixes | 2024-05-11 | 2024-06-15 | To Do | QA Team, End Users
Deployment & Go-Live | Final Deployment & Production Release | 2024-06-16 | 2024-06-30 | To Do | DevOps Team, IT Operations
Closure & Review | Post-Implementation Review & Documentation Finalization | 2024-07-01 | 2024-07-15 | To Do | Project Manager, Stakeholders