## Worksheet
Project Timeline - Process Documentation
Phase | Task Description | Start Date | End Date | Status | Responsible Person
Planning | Define project scope and objectives | 2023-10-01 | 2023-10-07 | Pending | Jane Doe
Design | Create system architecture and wireframes | 2023-10-08 | 2023-10-14 | In Progress | John Smith
Development | Build core features and modules | 2023-10-15 | 2023-11-05 | To Do | Alice Brown
Testing | Conduct unit and integration testing | 2023-11-06 | 2023-11-17 | To Do | Mike Johnson
Deployment | Deploy to production environment | 2023-11-18 | 2023-11-25 | To Do | Sarah Wilson
Review & Documentation | Finalize process documentation and post-mortem review | 2023-11-26 | 2023-12-03 | To Do | Jane Doe
Personal Use Template - Process Documentation ¦ Last Updated: 2023-10-01