## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Owner
T001 | Project Initiation | 2024-01-01 | 2024-01-15 | 15 | In Progress | Jane Doe
T002 | Requirements Gathering | 2024-01-16 | 2024-01-31 | 16 | To Do | John Smith
T003 | Design Phase | 2024-02-01 | 2024-02-15 | 15 | To Do | Sarah Lee
T004 | Development (Phase 1) | 2024-02-16 | 2024-03-15 | 30 | To Do | Mike Brown
T005 | Development (Phase 2) | 2024-03-16 | 2024-04-15 | 31 | To Do | Mike Brown
M001 | Milestone: Design Approval | 2024-02-15 | 2024-02-15 | 1 | Not Started | Sarah Lee
T006 | Testing & QA | 2024-04-16 | 2024-05-15 | 31 | To Do | Lisa White
M002 | Milestone: Final Testing Complete | 2024-05-15 | 2024-05-15 | 1 | Not Started | Lisa White
T007 | Deployment & Go-Live | 2024-05-16 | 2024-05-31 | 16 | To Do | Tom Wilson
M003 | Milestone: Project Completion | 2024-05-31 | 2024-05-31 | 1 | Not Started | All Team Members