## Worksheet
Project Timeline - Process Documentation
Phase / Milestone | Timeline |  |  | Responsible Team | Status
| Start Date | End Date | Duration (Days)
Project Initiation | 2024-01-05 | 2024-01-15 | 11 | Project Management Office (PMO) | Complete
Requirements Gathering | 2024-01-16 | 2024-01-31 | 16 | Business Analysts | In Progress
Design Phase | 2024-02-01 | 2024-02-15 | 15 | UX/UI Design Team | Pending
Development Sprint 1 | 2024-02-16 | 2024-03-01 | 14 | Software Development Team | Pending
Development Sprint 2 | 2024-03-02 | 2024-03-15 | 14 | Software Development Team | Pending
Testing & QA Phase | 2024-03-16 | 2024-04-15 | 31 | Quality Assurance Team | Pending
User Acceptance Testing (UAT) | 2024-04-16 | 2024-05-15 | 30 | End Users & Stakeholders | Pending
Deployment & Go-Live | 2024-05-16 | 2024-05-31 | 16 | IT Operations Team | Pending
Total Duration | 2024-01-05 to 2024-05-31 |  | 147 | Project Duration