## Worksheet
Project Timeline - Process Documentation
Phase / Task | Start Date | End Date | Status | Responsible Team | Description
Project Initiation & Planning | 2024-01-05 | 2024-01-15 | Completed | Project Management Office | Define project scope, objectives, stakeholders, and high-level timeline.
Requirements Gathering | 2024-01-16 | 2024-01-31 | Completed | Business Analysts, UX Team | Collect and document functional and non-functional requirements.
Design & Prototyping | 2024-02-01 | 2024-02-15 | In Progress | UI/UX Designers, Architects | Create wireframes, UI mockups, and system architecture diagrams.
Development Phase 1 | 2024-02-16 | 2024-03-15 | In Progress | Backend & Frontend Developers | Build core modules and integrate with backend services.
Testing & QA | 2024-03-16 | 2024-04-15 | Delayed | QA Team, DevOps Engineers | Execute unit, integration, system and user acceptance tests.
User Training & Documentation | 2024-04-16 | 2024-04-30 | Delayed | Training Coordinators, Technical Writers | Develop training materials and conduct sessions for end users.
Deployment & Go-Live | 2024-05-01 | 2024-05-15 | Delayed | DevOps, IT Operations | Deploy application to production environment and monitor post-launch.
Post-Implementation Review | 2024-05-16 | 2024-05-31 | Delayed | Project Manager, Stakeholders | Evaluate project success, document lessons learned.
This document is a professional project timeline template for process documentation. Last updated on2024-05-15.