## Worksheet
Project Timeline - Report VersionPurpose: Process Documentation
Phase/Task | Start Date | End Date | Status | Responsible Team | Dependencies | Notes / Comments
Project Initiation & Planning | 2025-01-05 | 2025-01-15 | In Progress | Project Management Office (PMO) | N/A | Define scope, objectives, and key milestones.
Requirements Gathering | 2025-01-16 | 2025-01-31 | Pending | Business Analysts & Stakeholders | Project Initiation & Planning | Collect all functional and non-functional requirements.
Design Phase | 2025-02-01 | 2025-02-14 | Pending | UX/UI Designers & Architects | Requirements Gathering Complete | Create wireframes, system architecture, and design documents.
Development & Implementation | 2025-02-15 | 2025-03-31 | Pending | Software Development Team | Design Phase Approved | Code development, module integration, and testing.
Quality Assurance & Testing | 2025-04-01 | 2025-04-15 | Pending | QA Team | Development & Implementation Complete | Perform system, integration, and UAT testing.
User Training & Documentation | 2025-04-16 | 2025-04-30 | Pending | Training Specialists & Technical Writers | Testing Phase Complete | Create training materials and process documentation.
Deployment & Go-Live | 2025-05-01 | 2025-05-10 | Pending | IT Operations & DevOps Team | User Training Complete | Final deployment to production environment.
Post-Implementation Review | 2025-05-11 | 2025-05-17 | Pending | Project Manager & Stakeholders | Go-Live Complete | Evaluate success, gather feedback, document lessons learned.
Total Duration: |  | 2025-01-05 to 2025-05-17