## Worksheet
Project Timeline - Small Business Process Documentation
Phase | Task | Start Date | End Date | Status | Responsible Person
Idea & Planning | Define Project Scope and Objectives | 2024-01-05 | 2024-01-15 | In Progress | Jane Smith
Idea & Planning | Stakeholder Alignment Meeting | 2024-01-16 | 2024-01-20 | Not Started | John Doe
Development | Design Prototype | 2024-01-21 | 2024-01-31 | Not Started | Alice Johnson
Development | Develop Core Features | 2024-02-01 | 2024-03-15 | Not Started | Mike Brown
Testing & Review | User Acceptance Testing (UAT) | 2024-03-16 | 2024-03-31 | Not Started | Sarah Wilson
Deployment | Finalize Documentation & Training Materials | 2024-04-01 | 2024-04-15 | Not Started | Lisa Garcia
Deployment | Launch Project & Monitor Performance | 2024-04-16 | 2024-05-31 | Not Started | All Team Members