## Worksheet
Project Timeline
Phase | Task | Start Date | End Date | Status | Owner(s)
Discovery & Planning | Market Research and User Persona Development | 2024-07-01 | 2024-07-15 | On Hold | Alice Chen, Mark Liu
Design & Prototyping | Wireframe Creation & UX Testing | 2024-07-16 | 2024-08-15 | In Progress | Sarah Kim, James Patel
Development Phase 1 | Frontend Development (MVP) | 2024-08-16 | 2024-09-30 | In Progress | Daniel Rojas, Olivia Moore
Development Phase 2 | Backend Integration & API Development | 2024-09-15 | 2024-10-31 | Not Started | Tina Wu, David Kim
QA & Testing | User Acceptance Testing (UAT) | 2024-11-01 | 2024-11-30 | Not Started | Lisa Tran, Ben Carter
Launch & Go-To-Market | Final Deployment & Marketing Campaign Launch | 2024-12-01 | 2024-12-31 | Not Started | Ryan Brown, Emily Wong