## Project Timeline - Team Use
Task ID | Task Description | Owner | Start Date | End Date | Status
T001 | Project Initiation & Planning | Project Manager | 2023-10-01 | 2023-10-15 | In Progress
T002 | Requirements Gathering | Business Analyst | 2023-10-16 | 2023-10-31 | Pending
T003 | Design Phase - UI/UX | UI/UX Designer | 2023-11-01 | 2023-11-15 | Pending
T004 | Development - Frontend | Frontend Developer | 2023-11-16 | 2024-01-31 | Pending
T005 | Development - Backend | Backend Developer | 2023-11-16 | 2024-01-31 | Pending
T006 | Integration Testing | QA Engineer | 2024-02-01 | 2024-02-15 | Pending
T007 | User Acceptance Testing (UAT) | Stakeholders & End Users | 2024-02-16 | 2024-03-15 | Pending
M01 | Project Launch & Go-Live | Project Manager | 2024-03-16 | 2024-03-16 | Pending
T008 | Post-Launch Review & Documentation Finalization | Project Manager & Team | 2024-03-17 | 2024-03-31 | Pending
Notes:This timeline is for team use and will be updated weekly. Status updates to be confirmed by task owners.