## Worksheet
Project Timeline - Tracking View
Process Documentation Template
Phase / Task | Start Date | End Date | Status | Responsible Party | Progress (%)
Project Initiation & Planning | 2023-10-01 | 2023-10-15 | Completed | Jane Smith | 100%
Requirement Gathering | 2023-10-16 | 2023-10-31 | Completed | John Doe | 100%
Design Phase | 2023-11-01 | 2023-11-25 | In Progress | Sarah Lee | 75%
Development - Frontend | 2023-11-26 | 2024-01-15 | Pending | Mike Chen | 0%
Development - Backend | 2023-11-26 | 2024-01-31 | Pending | Alex Rodriguez | 0%
Testing & QA | 2024-02-01 | 2024-03-15 | Pending | Lisa Park | 0%
User Training & Documentation | 2024-03-16 | 2024-03-31 | Pending | Emma Wilson | 0%
Deployment & Go-Live | 2024-04-01 | 2024-04-15 | Pending | James Brown | 0%
Total Project Duration | 2023-10-01 to 2024-04-15 |  | In Progress | Overall Progress: 65%
Last Updated: April 5, 2024 ¦ Generated from Process Documentation System