## Worksheet
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Progress (%)
TASK001 | Project Initiation & Planning | Jane Doe | In Progress | 2023-10-01 | 2023-10-15 | 75
TASK002 | Requirements Gathering | John Smith | To Do | 2023-10-16 | 2023-10-31 | 0
TASK003 | Design Phase - UI/UX | Alice Johnson | Not Started | 2023-11-01 | 2023-11-15 | 0
TASK004 | Development - Backend | Mike Brown | Status: In Progress | Start Date: 2023-11-16 | End Date: 2024-01-31 | 50
TASK005 | Testing & QA | Sarah Wilson | Status: Not Started | Start Date: 2024-02-01 | End Date: 2024-03-15 | 0
TASK006 | Deployment & Go-Live | Robert Taylor | Status: Not Started | Start Date: 2024-03-16 | End Date: 2024-04-30 | 0