## Worksheet
Project Tracker - Extended Template
Process Documentation ¦ Version 2.0
Project ID | Project Name | Key Milestones |  |  | Owner | Status | Progress (%) | Deadline | Actions/Notes
|  | Initiation Date | Completion Target | Actual Completion
P001 | Website Redesign Phase 1 | 2024-03-05 | 2024-05-15 | --/--/---- | Jane Doe | In Progress | 68% | 2024-05-15 | Final wireframes approved. Design phase ongoing.
P002 | Cybersecurity Audit Upgrade | 2024-01-15 | 2024-04-30 | 2024-04-18 | John Smith | Completed | 100% | 2024-04-30 | Audit passed with zero critical vulnerabilities.
P003 | Customer Portal Integration | 2024-04-15 | 2024-11-30 | --/--/---- | Lisa Wang | Pending | 8% | 2024-11-30 | API specs pending client approval.
P004 | Internal Training Platform Launch | 2023-11-15 | 2024-07-31 | --/--/---- | Mike Torres | In Progress | 45% | 2024-07-31 | Content development 60% complete.
P005 | Cloud Migration Phase II | 2024-02-18 | 2024-12-31 | --/--/---- | Sarah Kim | Delayed | 30% | 2024-12-31 | Infrastructure bottleneck identified. Vendor escalation underway.
P006 | Data Analytics Dashboard Revamp | 2024-03-18 | 2024-11-31 | --/--/---- | Alex Rivera | Pending | 5% | 2024-11-30 | Requirement gathering in progress.
P007 | Mobile App v3.0 Release | 2024-04-15 | 2025-12-31 | --/--/---- | Nina Patel | In Progress | 78% | 2025-12-31 | User testing phase to begin Q3 2024.
P008 | HR Onboarding Automation | 2024-11-15 | 2025-03-31 | --/--/---- | Daniel Brooks | Pending | 0% | 2025-03-31 | Stakeholder approval pending.
P009 | Sustainability Reporting System | 2024-12-15 | 2025-11-30 | --/--/---- | Elena Lopez | Pending | 2% | 2025-11-30 | Budget approval delayed.
P010 | API Gateway Redesign | 2024-05-25 | 2025-12-31 | --/--/---- | Karen Chen | In Progress | 47% | 2025-12-31 | Architecture phase completed. Development underway.