## Worksheet
Project ID | Project Name | Department | Status | Start Date | Planned End Date | Actual End Date | % Complete | Budget (USD) | Actual Spend (USD)
PROJ-001 | Website Redesign Initiative | Marketing | In Progress | 2024-03-01 | 2024-05-31 | - | 75% | 15,000 | 11,250
PROJ-002 | CRM System Integration | IT Operations | On Hold | 2024-03-15 | 2024-07-15 | - | 35% | 38,000 | 13,300
PROJ-004 | User Experience Testing Phase | Product Development | Completed | 2024-01-15 | 2024-03-31 | 2024-03-31 | 100% | 8,500 | 8,567
PROJ-012 | Data Migration Project | IT Infrastructure | Pending Approval | 2024-03-25 | - | -
Total Projects: | [8 empty] | 4
Note:This is a monthly project tracker template for process documentation. Update status, dates, and financials as per progress.
Generated on: