## Worksheet
Task ID | Task Description | Assigned To | Status | Start Date | Due Date | Progress (%)
PJ001 | Define project scope and objectives | Jane Doe | In Progress | 2023-09-15 | 2023-09-30 | 65%
PJ002 | Develop initial wireframes | John Smith | Pending | 2023-10-01 | 2023-10-15 | 5%
PJ003 | Review and finalize design mockups | Sarah Wilson | In Progress | 2023-10-05 | 2023-10-18 | 45%
PJ004 | Frontend development phase 1 | Mike Brown | Pending | 2023-10-15 | 2023-11-05 | 0%
PJ005 | Backend API integration | Lisa Chen | In Progress | 2023-10-10 | 2023-11-08 | 75%
PJ006 | User testing and feedback collection | James Reed | Pending | 2023-11-15 | 2023-11-30 | 0%
PJ007 | Final deployment and release | Tina Lopez | Pending | 2023-12-01 | 2023-12-15 | 0%
Project Summary
Total Tasks:7
In Progress:3 (42.9%)
Pending:3 (42.9%)
Completed:1 (14.3%)