## Worksheet
Week | Project Name | Task Description | Status | Assigned To | Start Date | End Date
Week 1 | Website Redesign Project | Create wireframes for homepage and key pages | In Progress | Jane Smith | 2023-10-02 | 2023-10-15
Week 1 | Data Migration Initiative | Assess current database schema and identify migration risks | To Do | John Doe | 2023-10-02 | 2023-10-14
Week 2 | Website Redesign Project | Review and approve wireframes with stakeholders | In Progress | Jane Smith, Alex Johnson | 2023-10-16 | 2023-10-29
Week 2 | Data Migration Initiative | Develop migration plan and timeline proposal | In Progress | John Doe, Maria Garcia | 2023-10-16 | 2023-10-30
Week 3 | Website Redesign Project | Begin frontend development for homepage | To Do | Lisa Wang | 2023-10-30 | 2023-11-14
Week 3 | Data Migration Initiative | Finalize migration plan and get approval from IT leadership | To Do | John Doe, Maria Garcia, Tom Lee | 2023-10-30 | 2023-11-17