## Worksheet
Process Documentation - Schedule Planner (Analysis View)
Activity ID | Task Description | Responsible Party | Start Date | End Date | Status | Duration (Days) | Dependencies | Milestone Flag | Risk Level | Effort (Hours) | Notes
A001 | Requirement Gathering | Business Analyst Team | 2025-04-01 | 2025-04-15 | In Progress | 15 | None | Yes | Medium | 80 | User interviews scheduled weekly.
A002 | Process Analysis & Mapping | Process Owner | 2025-04-16 | 2025-04-30 | To Do | 15 | A001 Complete | No | Low | 60 | Map current state workflow.
A003 | System Design Phase | IT Architects | 2025-05-01 | 2025-06-15 | To Do | 46 | A002 Complete | No | High | 180 | Include security and scalability considerations.
A004 | Development & Coding | Development Team | 2025-06-16 | 2025-08-31 | In Progress | 77 | A003 Complete | No | Medium | 450 | Daily sprint reviews in place.
A005 | Testing & Validation | QA Team | 2025-09-01 | 2025-11-30 | To Do | 91 | A004 Complete | No | High | 360
A006 | User Training & Documentation | Training Specialist | 2025-12-01 | 2025-12-31 | To Do | 31 | A005 Complete | Yes | Low | 80
A007 | Go-Live & Deployment | IT Operations | 2026-01-01 | 2026-01-31 | To Do | 31 | A006 Complete | Yes
This schedule planner is designed for analysis and monitoring of process documentation timelines. All dates are projected based on current estimates.