## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Assigned To | Description
TASK001 | Project Initiation | 2023-10-01 | 2023-10-05 | In Progress | John Doe | Define project scope and objectives.
TASK002 | Requirements Gathering | 2023-10-06 | 2023-10-15 | Not Started | Jane Smith | Capture all functional and non-functional requirements.
TASK003 | Design Phase | 2023-10-16 | 2023-10-25 | Not Started | Mike Johnson | Create system architecture and UI mockups.
TASK004 | Development | 2023-10-26 | 2023-11-15 | Not Started | Sarah Lee | Implement core features based on design.
TASK005 | Testing | 2023-11-16 | 2023-11-30 | Not Started | David Brown | Conduct unit, integration, and system testing.
TASK006 | Deployment | 2023-12-01 | 2023-12-05 | Not Started | Lisa Wang | Deploy system to production environment.
TASK007 | Post-Implementation Review | 2023-12-06 | 2023-12-10 | Not Started | All Team Members | Evaluate project success and document lessons learned.