## Worksheet
Process Step | Task Description | Owner/Responsible | Start Date | End Date | Status | Dependencies
Planning Phase
1.1 | Define project scope and objectives | Project Manager | 2023-09-01 | 2023-09-05 | To Do | N/A
1.2 | Identify key stakeholders and requirements | Business Analyst | 2023-09-06 | 2023-09-10 | In Progress | 1.1 Complete
1.3 | Create initial project schedule and milestones | Project Manager | 2023-09-11 | 2023-09-15 | To Do | 1.2 Complete
Execution Phase
2.1 | Develop process documentation templates | Documentation Specialist | 2023-09-16 | 2023-09-25 | To Do | 1.3 Complete
2.2 | Conduct stakeholder workshops for process validation | Business Analyst, Project Manager | 2023-09-26 | 2023-10-05 | In Progress | 2.1 Complete
2.3 | Finalize process documentation and review with team leads | Documentation Specialist, Team Leads | 2023-10-06 | 2023-10-15 | In Progress | 2.2 Complete
Closure Phase
3.1 | Submit final documentation package to stakeholders | Project Manager | 2023-10-16 | 2023-10-20 | To Do | 2.3 Complete
3.2 | Conduct post-implementation review and feedback session | Project Manager, Team Leads | 2023-10-21 | 2023-10-25 | In Progress | 3.1 Complete
Overall Project Status: | [5 empty] | On Track (75% Complete)