## Worksheet
Process Documentation - Schedule Planner (Financial View)
Phase | Task Description | Start Date | End Date | Budget ($) | Status
Phase 1: Initiation | Define Project Scope & Objectives | 2025-04-01 | 2025-04-10 | 8,500.00 | In Progress
Phase 1: Initiation | Stakeholder Alignment Workshop | 2025-04-11 | 2025-04-15 | 3,750.00 | Pending Approval
Phase 2: Planning | Develop Detailed Project Plan | 2025-04-16 | 2025-04-30 | 15,800.00 | Not Started
Phase 2: Planning | Risk Assessment & Mitigation Strategy | 2025-05-01 | 2025-05-10 | 7,450.00 | Not Started
Phase 3: Execution | Resource Allocation & Team Onboarding | 2025-05-11 | 2025-06-15 | 48,900.00 | In Progress
Phase 3: Execution | Development & Implementation Phase 1 | 2025-06-16 | 2025-07-31 | 89,750.00 | In Progress
Phase 4: Monitoring & Control | Weekly Status Meetings & Reporting | 2025-05-11 | 2025-08-31 | 6,950.00 | In Progress
Phase 4: Monitoring & Control | Budget Performance Review (Monthly) | 2025-06-01 | 2025-08-31 | 4,375.00 | In Progress
Phase 5: Closure | Final Deliverables Handover & Acceptance | 2025-09-01 | 2025-09-15 | 14,875.00 | Not Started
Phase 5: Closure | Closure Documentation & Lessons Learned | 2025-09-16 | 2025-09-30 | 8,475.00 | Not Started
Total Project Cost: |  |  |  | $219,825.00
Notes:This schedule planner is designed for financial tracking and project timeline management. All dates are in YYYY-MM-DD format. Status indicators reflect real-time progress updates.