## Worksheet
PROCESS DOCUMENTATION - SCHEDULE PLANNER (Large Business Style)
Task ID | Task Name | Department | Owner | Start Date | End Date | Status | Milestone? | Budget (USD)
PRJ-001 | Project Initiation & Planning | Executive Management | Jane Doe | 2024-01-15 | 2024-01-31 | Pending | Yes | $5,500.00
PRJ-002 | Requirements Gathering | Product Development | John Smith | 2024-02-01 | 2024-03-15 | In Progress | Yes | $8,750.00
PRJ-003 | Design Phase - UI/UX | Design Team | Alice Johnson | 2024-03-16 | 2024-05-10 | In Progress | Yes | $15,300.00
PRJ-004 | Development & Coding | Engineering | Robert Brown | 2024-05-11 | 2024-08-31 | On Track | No | $75,800.00
PRJ-005 | Testing & QA Validation | Quality Assurance | Lisa White | 2024-09-01 | 2024-10-15 | On Track | Yes | $36,500.00
PRJ-006 | Deployment & Go-Live | IT Operations | Mark Lee | 2024-10-16 | 2024-11-30 | On Track | Yes | $55,900.00
PRJ-007 | Post-Launch Review | Project Management Office | Sarah Chen | 2024-12-01 | 2024-12-31 | Pending | Yes | $8,450.00