## Worksheet
Process Documentation - Schedule Planner
Multi-Page Template Version 1.0
Date | Task Name | Responsible Party | Timeline |  |  | Status | Notes / Comments
|  |  | Start Date | End Date | Duration (Days)
2023-10-05 | Project Kickoff Meeting | Project Manager | 2023-10-05 | 2023-10-05 | 1 | In Progress | Initial planning and team alignment.
2023-10-06 | Requirements Gathering | Business Analyst | 2023-10-06 | 2023-10-15 | 10 | Pending | Capture all functional and non-functional requirements.
2023-10-16 | System Design Phase | Lead Architect | 2023-10-16 | 2023-10-31 | 16 | To Do | Create high-level and detailed system architecture.
2023-11-01 | Development Sprint 1 | Development Team | 2023-11-01 | 2023-11-14 | 14 | To Do | Implement core modules based on design.
2023-11-15 | Testing Phase (Sprint 1) | QA Team | 2023-11-15 | 2023-11-30 | 16 | To Do | Conduct unit, integration, and system testing.
2023-12-01 | UAT (User Acceptance Testing) | Stakeholders & End Users | 2023-12-01 | 2023-12-15 | 15 | To Do | Gather feedback and validate system readiness.
2023-12-16 | Final Review & Signoff | Project Sponsor | 2023-12-16 | 2023-12-18 | 3 | To Do | Final approval before deployment.
2023-12-19 | Deployment to Production | DevOps Team | 2023-12-19 | 2023-12-19 | 1 | To Do | Cutover to production environment.
2023-12-20 | Post-Deployment Review | Project Manager | 2023-12-20 | 2023-12-21 | 2 | To Do | Evaluate performance and lessons learned.
2023-12-25 | Maintenance & Support Phase Start | Support Team | 2023-12-25 | ∞ | Ongoing | To Do | Monitor system, handle incidents, and apply patches.
© 2023 Process Documentation Team ¦ Multi-Page Schedule Planner Template v1.0
Process Documentation - Schedule Planner (Continued)
Multi-Page Template Version 1.0
Task ID | Dependency (Predecessor) | Resource Allocation | Progress Tracking |  |  | Risk Level
|  |  | Planned (%) | Actual (%) | Comments on Deviation
T001 | - | Project Manager, 100%; Analyst, 50% | 10 | 8 | Slight delay due to stakeholder availability. | Moderate
T002 | T001 | BA, 100% | 50 | 45 | N/A (on track)
T003 | T002 | Architect, 100% | 75 | 72 | N/A (minor delay)
T004 | T003 | Dev Team, 125% | 65 | 68 | N/A (slight ahead of schedule)
T005 | T004 | QA Lead, 100% | 30 | 28 | N/A (in line)
T006 | T005 | End Users, 15% | 45 | 42 | N/A (minor delay)
T007 | T006 | Sponsor, 10% | 85 | 85 | N/A (on schedule)
T008 | T007 | DevOps, 15% | 95 | 92 | N/A (minor lag)
T009 | T008 | PM, 35% | 100 | 100 | N/A (completed)
T999 | - | Support Team, 25% | 0 | 0 | N/A (future phase)
© 2023 Process Documentation Team ¦ Multi-Page Schedule Planner Template v1.0
Process Documentation - Schedule Planner (Final Page)
Multi-Page Template Version 1.0
Project Summary & Key Metrics
Total Tasks: | 10 | Completed: | 1 (T999 is pending) | Overall Progress:85%
Budget (Est.): | $250,000 | Budget Used: | $175,643
Planned Duration: | 92 days | Elapsed Time: | 40 days (as of 2023-11-05)
Risk Assessment Summary
High-Risk Items: | 3 | Moderate-Risk Items: | 4 | Risk Legend:HighModerateLow
Next Steps & Recommendations
• Accelerate UAT by scheduling additional feedback sessions. • Assign dedicated support staff for post-deployment monitoring. • Conduct a full retrospective after project closure to capture lessons learned. • Update resource allocation based on actual progress trends.