## Worksheet
Process Documentation - Schedule Planner
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Priority
T001 | Project Kickoff Meeting | Jane Doe | 2023-10-05 | 2023-10-05 | Completed | High
T002 | Requirements Gathering | John Smith | 2023-10-06 | 2023-10-15 | In Progress | High
T003 | Design Phase - Wireframes | Alice Johnson | 2023-10-16 | 2023-10-25 | Not Started | Medium
T004 | Development - Frontend | Mike Brown | 2023-10-26 | 2023-11-15 | Not Started | High
T005 | Development - Backend | Sarah Wilson | 2023-10-26 | 2023-11-20 | Not Started | High
T006 | User Testing & Feedback | Lisa Taylor | 2023-11-21 | 2023-11-30 | Not Started | Medium
T007 | Final Review & Deployment | Jane Doe | 2023-12-01 | 2023-12-05 | Not Started | High
Note:This schedule planner is designed for one-page visibility and real-time tracking. Update status regularly to maintain project transparency.