## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Status
T001 | Requirements Gathering | John Doe | 2025-04-01 | 2025-04-07 | In Progress
T002 | Design Phase - Wireframes | Jane Smith | 2025-04-08 | 2025-04-14 | Not Started
T003 | Development - Frontend | Mike Johnson | 2025-04-15 | 2025-04-30 | Not Started
T004 | Development - Backend | Lisa Brown | 2025-04-15 | 2025-05-15 | Not Started
T005 | Testing & QA | Robert Clark | 2025-05-16 | 2025-06-10 | Not Started
T006 | User Training & Documentation | Sarah Wilson | 2025-06-11 | 2025-06-18 | Not Started
T007 | Go-Live & Deployment | James Taylor | 2025-06-19 | 2025-06-25 | Not Started