## Worksheet
Process Documentation - Schedule Planner
Task ID | Task Description | Responsible Team/Person | Start Date | End Date | Status | Priority Level
T001 | Project Kickoff Meeting | Project Manager, Team Leads | 2023-10-05 | 2023-10-05 | Completed | High
T002 | Requirement Gathering & Analysis | Business Analysts, UX Designers | 2023-10-06 | 2023-10-15 | In Progress | High
T003 | System Design & Architecture Review | Lead Developers, Architects | 2023-10-16 | 2023-10-25 | Pending | High
T004 | UI/UX Design Development | Design Team, Frontend Developers | 2023-10-26 | 2023-11-15 | Pending | Medium
T005 | Backend Development Phase 1 | Backend Developers, DevOps Team | 2023-11-16 | 2023-12-15 | Pending | High
T006 | Frontend Development Phase 1 | Frontend Developers, QA Team (Prep) | 2023-12-16 | 2024-01-15 | Pending | Medium
T007 | Integration Testing & Debugging | QA Team, Developers | 2024-01-16 | 2024-01-31 | Pending | High
T008 | User Acceptance Testing (UAT) | End Users, Business Analysts, QA Team | 2024-02-01 | 2024-02-15 | Pending | High
T009 | Final Deployment & Go-Live Preparation | DevOps, Project Manager, Support Team | 2024-02-16 | 2024-02-25 | Pending | High
T010 | Post-Launch Review & Documentation Finalization | All Stakeholders, Project Manager | 2024-02-26 | 2024-03-15 | Pending | Medium