## Worksheet
Process Documentation - Schedule Planner (Report Version)
Task ID | Task Name | Department/Owner | Schedule Details |  |  | Status | Duration (Days)
|  |  | Start Date | End Date | Priority
TP001 | Requirements Gathering | Product Team | 2024-05-15 | 2024-05-23 | Highest | In Progress | 9
TP002 | Design Phase (UI/UX) | Design Team | 2024-05-24 | 2024-06-15 | High | Pending Approval | 23
TP003 | Development Sprint 1 | Development Team | 2024-06-16 | 2024-07-14 | High | Not Started | 30
TP004 | Testing & QA Cycle 1 | QA Team | 2024-07-15 | 2024-08-15 | Medium | Not Started | 31
TP005 | User Acceptance Testing (UAT) | Stakeholders & Ops Team | 2024-08-16 | 2024-09-15 | High | Not Started | 31
TP006 | Deployment & Go-Live Preparation | IT Operations | 2024-09-16 | 2024-10-15 | Highest | Not Started | 30
Total Duration: |  |  |  |  | 154 days
Report Generated on: 2024-05-10 ¦ Version: 1.3 ¦ Prepared by: Process Documentation Team