## Worksheet
Task ID | Task Name | Responsible Team | Start Date | End Date | Status | Duration (Days)
T001 | Requirements Gathering | Business Analysts | 2023-10-02 | 2023-10-15 | In Progress | 14
T002 | System Design Phase | IT Architects | 2023-10-16 | 2023-11-05 | Pending | 20
T003 | Development Sprint 1 | Development Team | 2023-11-06 | 2023-11-25 | Pending | 20
T004 | Testing & QA Validation | QA Engineers | 2023-11-26 | 2023-12-15 | Pending | 20
T005 | User Training & Documentation | Training Team | 2023-12-16 | 2024-01-15 | Pending | 31
T006 | Go-Live & Deployment | Operations Team | 2024-01-16 | 2024-01-31 | Pending | 16
T007 | Post-Implementation Review | Project Manager | 2024-02-01 | 2024-02-15 | Pending | 15
Note:This is a summary view of the process documentation schedule. Status updates are subject to change.