## Worksheet
Week | Task ID | Task Description | Assigned To | Status | Start Date | Due Date
Week 1 | T001 | Review project requirements document | Jane Doe | In Progress | 2023-10-02 | 2023-10-06
Week 1 | T002 | Create initial task list and timeline | John Smith | Not Started | 2023-10-02 | 2023-10-05
Week 2 | T003 | Conduct stakeholder meeting | Jane Doe | Completed | 2023-10-09 | 2023-10-11
Week 2 | T004 | Develop process workflow diagrams | John Smith | In Progress | 2023-10-09 | 2023-10-15
Week 3 | T005 | Review and finalize documentation draft | Jane Doe | Not Started | 2023-10-16 | 2023-10-20
Week 3 | T006 | Share final documentation with team for feedback | John Smith | Not Started | 2023-10-16 | 2023-10-18
Week 4 | T007 | Implement feedback and publish final version | Jane Doe | Not Started | 2023-10-23 | 2023-10-27
Week 4 | T008 | Archive completed documentation and close task list | John Smith | Not Started | 2023-10-23 | 2023-10-31