## Worksheet
Process Documentation - Time Tracker (Planning View)
Project/Task | Phase | Start Date | End Date | Estimated Hours | Status | Assigned To | Planned Schedule (Weeks)
Planning Timeline View - Weekly Breakdown
Phase 1: Requirements Gathering
Review Stakeholder Needs | Requirements | 2024-04-01 | 2024-04-15 | 36 | In Progress | John Doe | Week 1 | Week 2 | Week 3
Document Functional Specs | Requirements | 2024-04-16 | 2024-05-03 | 88 | In Progress | Jane Smith | Week 4 | Week 5 | Week 6
Review & Approve Specs | Requirements | 2024-05-06 | 2024-05-17 | 48 | Pending Approval | Project Lead | Week 7 | Week 8 | Week 9
Phase 2: Design & Prototyping
UI/UX Wireframes | Design | 2024-05-18 | 2024-06-14 | 96 | Not Started | Alex Chen | Week 10 | Week 11 | Week 12
Prototype Development | Design | 2024-06-17 | 2024-07-19 | 136 | Not Started | Maria Gonzalez | Week 13 | Week 14 | Week 15
Total Estimated Hours: |  |  |  | 504