## Worksheet
Process Documentation - To-Do List (Client View)
Task ID | Task Description | Assigned To | Status | Prioritization | Due Date
TASK001 | Review project requirements document and provide feedback. | Client Liaison Team | Pending | High | 2025-04-15
TASK002 | Confirm approval of initial design mockups. | Project Manager - Client | In Progress | High | 2025-04-18
TASK003 | Provide input on user interface usability testing results. | Client UX Reviewer | Pending | Medium | 2025-04-20
TASK004 | Finalize content for client onboarding email series. | Content Team - Client | In Progress | Medium | 2025-04-17
TASK005 | Approve final version of the project timeline. | Client Stakeholder Lead | Pending | High | 2025-04-16
TASK006 | Review and sign off on final deliverables package. | Client Executive | Pending | High | 2025-04-25
TASK007 | Provide feedback on post-launch support plan. | Client Operations Lead | Pending | Low | 2025-04-30
Last Updated:April 5, 2025 ¦Version:1.1