## Worksheet
Process Documentation - Manager View (To-Do List)
Task ID | Task Description | Assigned To | Status | Priority | Due Date | Progress (%)(0-100)
TASK-001 | Review project requirements document | John Smith | In Progress | High | 2024-04-15 | 65%
TASK-002 | Develop user authentication module | Alice Johnson | Pending | High | 2024-04-18 | 0%
TASK-003 | Conduct team sprint planning meeting | Michael Brown | Completed | Medium | 2024-04-10 | 100%
TASK-004 | Update process documentation for onboarding | Sarah Lee | In Progress | Medium | 2024-04-17 | 80%
TASK-005 | Perform system integration testing | Robert Davis | Pending | High | 2024-04-19 | 0%
TASK-006 | Review QA feedback from previous sprint | Linda Wilson | Completed | Low | 2024-04-11 | 100%