## Worksheet
Annual Weekly Planner - Process Documentation
Week | Start Date | End Date | Objective / Focus Area | Status (Complete/In Progress/Pending) | Tasks / Activities
Week 1: January 1 - January 7
Week 01 | Jan-01-2024 | Jan-07-2024 | Project Kickoff & Planning | Pending | Finalize project scope Assign team roles and responsibilities Create initial documentation baseline
Week 2: January 8 - January 14
Week 02 | Jan-08-2024 | Jan-14-2024 | Documentation Phase I - Requirements Gathering | In Progress | Capture functional requirements from stakeholders Conduct initial process mapping sessions Update requirements traceability matrix (RTM)
Week 3: January 15 - January 21
Week 03 | Jan-15-2024 | Jan-21-2024 | Process Design & Approval Workshops | Pending | Develop initial process flowcharts Schedule design review meetings with SMEs Document feedback and revisions in change log
Week 4: January 22 - January 28
Week 04 | Jan-22-2024 | Jan-28-2024 | Documentation Finalization & Peer Review | Pending | Compile all process documents into a master repository Conduct peer review sessions with cross-functional team leads Update version control and release notes
Week 5: January 29 - February 4
Week 05 | Jan-29-2024 | Feb-04-2024 | User Training Preparation | Pending | Create training materials (manuals, slides) Identify key user groups for onboarding sessions Develop assessment tools for knowledge validation
Week 6: February 5 - February 11
Week 06 | Feb-05-2024 | Feb-11-2024 | User Training & Onboarding (Phase I) | Pending | Deliver training sessions for department A and B Collect feedback forms post-training Address knowledge gaps with supplementary materials
Week 7: February 12 - February 18
Week 07 | Feb-12-2024 | Feb-18-2024 | User Training & Onboarding (Phase II) | Pending | Deliver training sessions for department C and D Conduct live Q&A sessions for clarification Update process documents based on training insights
Week 8: February 19 - February 25
Week 08 | Feb-19-2024 | Feb-25-2024 | Pilot Run & Feedback Collection | Pending | Initiate pilot implementation with 3 core teams Monitor process execution for bottlenecks Collect qualitative and quantitative feedback daily
Week 9: February 26 - March 3
Week 09 | Feb-26-2024 | Mar-03-2024 | Pilot Review & Process Optimization | Pending | Analyze pilot data and feedback reports Identify process improvement opportunities (PIs) Update documentation with optimized workflows
Week 10: March 4 - March 10
Week 10 | Mar-04-2024 | Mar-10-2024 | System Integration & Validation Testing | Pending | Integrate process documentation with ERP/CRM systems Conduct end-to-end test scenarios in staging environment Validate data accuracy and workflow continuity across modules
Week 11: March 11 - March 17
Week 02 | Mar-04-2024 | Mar-17-2024 | Certification Readiness & Audit Preparation | Pending | Prepare audit checklist and compliance evidence pack Conduct mock audit with internal QA team Address findings before external certification review
Week 12: March 18 - March 24
Week 03 | Mar-04-2024 | Mar-31-2024 | Certification Submission & External Review | Pending | Submit documentation package to certifying body Coordinate response to external auditor questions Prepare for on-site or virtual assessment visit if required
Additional Weeks (March 25 - December 31, 2024)
Additional weekly entries will follow the same format through December 31, 2024. Each week includes objective tracking, task lists, and status updates for continuous process documentation and improvement.