## Worksheet
Weekly Planner - Detailed Process Documentation
Day & Date | Task / Activity | Process Step Description | Status (Pending/In Progress/Completed) | Owner / Responsible Party | Estimated Time (hrs) | Actual Time (hrs) | Notes / Comments
Monday, April 1, 2024 | Project Kickoff Meeting | Initiate new project with stakeholders. Define objectives, scope, deliverables and success criteria. | Pending | Alice Johnson (Project Lead) | 2 |  | Agenda shared via email.
Tuesday, April 2, 2024 | Data Collection & Validation | Gather input data from relevant departments. Validate accuracy and completeness before processing. | In Progress | Robert Chen (Data Analyst) | 3.5 |  | Received 87% of required data; follow-up with Finance team.
Wednesday, April 3, 2024 | Workflow Design Phase | Create detailed process flow diagrams and document handoff points between teams. | Pending | Lisa Wong (Process Designer) | 4 |  | Templates approved by PMO.
Thursday, April 4, 2024 | Risk Assessment Workshop | Analyze potential risks in the process. Develop mitigation strategies for high-impact areas. | Completed | James Reed (Risk Manager) | 3 | 2.75 | All risks documented; action items assigned.
Friday, April 5, 2024 | Draft Process Documentation | Compile all process steps into a formal document with visuals and version control. | Pending | Sophia Martinez (Documentation Specialist) | 5.0Review draft by team leads on Monday.
Week Summary
Total Estimated Time: |  |  | 17.5 hours |  |  | Total Actual Time (Logged): | 2.75 hours