## Weekly Planner - Tracking View
Weekly Planner - Tracking View
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete | Notes/Progress Update
T001 | Review project requirements | Jane Doe | 2024-04-01 | 2024-04-03 | In Progress | 65% | Initial analysis complete. Awaiting feedback from stakeholders.
T002 | Design system architecture | John Smith | 2024-04-02 | 2024-04-05 | To Do | 15% | Preliminary sketches in progress.
T003 | Develop front-end UI components | Alice Johnson | 2024-04-01 | 2024-04-15 | In Progress | 38% | Completed 5 of 12 components.
T004 | Backend API integration testing | Robert Brown | 2024-04-08 | 2024-04-11 | Blocked | 5% | Awaiting server configuration update.
T005 | Finalize documentation and user guide | Sarah Wilson | 2024-04-12 | 2024-04-18 | To Do | 0% | Documentation template reviewed.