## Worksheet
Task | Responsible Party | Start Date | End Date | Allocated Budget | Status | Progress (%)
Market Research & Analysis | Marketing Team | 2024-03-15 | 2024-04-10 | $5,000 | In Progress | 65%
Product Feature Development | Engineering Team | 2024-03-20 | 2024-05-15 | $18,000 | Not Started | 0%
User Training & Onboarding | HR & Support Team | 2024-04-01 | 2024-04-30 | $3,500 | Planned | 10%
Performance Optimization | Engineering Team | 2024-05-01 | 2024-06-15 | $7,000 | Not Started | 0%
Monthly Review & Reporting | Project Manager | 2024-01-01 | Ongoing | $2,500 (Monthly) | Ongoing | 85%