## Worksheet
Task | Assigned To | Start Date | End Date | Status | Progress (%) | Budget Allocated ($) | Actual Spend ($) | Remaining Budget ($)
Market Research & Analysis | Sarah Johnson | 2024-03-15 | 2024-04-10 | In Progress | 65% | 2,500 | 1,800 | 700
Product Development Planning | Michael Chen | 2024-03-20 | 2024-05-15 | Not Started | 0% | 8,000 | 0 | 8,000
User Experience Design Review | Anna Rodriguez | 2024-04-01 | 2024-04-30 | Completed | 100% | 3,200 | 3,200 | 0
Team Training & Onboarding | David Kim | 2024-03-25 | 2024-04-15 | In Progress | 75% | 1,500 | 1,125 | 375
Performance Metrics Setup | Linda Patel | 2024-03-30 | 2024-05-05 | Not Started | 0% | 4,000 | 0 | 4,000
Total Budget Allocated: |  |  |  | 28,700 | Total Actual Spend: |  |  | 6,125