## Worksheet
Week | Objective | Key Actions | Responsible Party | Deadline | Progress (%) | Risks & Mitigation
Week 1 | Define core productivity goals | Conduct team survey; identify pain points; draft KPIs | Productivity Officer | 2024-04-07 | 50% | Risks: Low engagement. Mitigation: Incentivize participation with recognition.
Week 2 | Implement time-blocking strategy | Train team on time-blocking; assign daily schedules | Team Leads & HR | 2024-04-14 | 30% | Risks: Resistance to change. Mitigation: Offer flexibility and support sessions.
Week 3 | Introduce task prioritization framework | Adopt Eisenhower Matrix; update project planning tools | Project Manager | 2024-04-21 | 25% | Risks: Misclassification of tasks. Mitigation: Weekly review with team lead.
Week 4 | Measure and analyze productivity metrics | Collect data on output, meeting efficiency, focus time | Data Analyst & Team Leads | 2024-04-28 | 10%