## Worksheet
Productivity Improvement Business Template (Advanced Version)
Task/Activity | Owner | Target Deadline | Status | Current Progress (%) | Resources Required th> | Risks & Dependencies | Action Items
Define Key Performance Indicators (KPIs) | John Doe (Operations Manager) | 2024-03-15 | In Progress | 65% | Budget: $1,500; Tools: Excel, Power BI | Uncertain data source availability | Finalize KPIs by end of month; present to leadership team.
Optimize Daily Workflows | Jane Smith (HR Director) | 2024-04-01 | Pending Review | 30% | Budget: $2,000; Tools: Workflow software, time tracking app | Team resistance to change; training required | Conduct staff workshop; develop training plan.
Implement Time-Blocking System | Michael Lee (Project Lead) | 2024-03-30 | Not Started | 0% | Budget: $500; Tools: Calendar, task manager | No alignment with team schedules yet | Host pilot session with 3 teams; collect feedback.
Conduct Productivity Audit | Sarah Chen (Finance Officer) | 2024-04-10 | Completed | 100% | Budget: $3,200; Tools: Analytics platform, surveys | Data privacy concerns resolved | Report submitted to executive committee.
Set Monthly Review Meetings | All Managers (Cross-functional) | 2024-03-25 | In Progress | 70% | Budget: $0; Tools: Zoom, shared calendar | Need to finalize meeting agendas | Distribute agenda templates and assign facilitators.