## Worksheet
Date | Task | Assigned To | Priority | Status | Progress (%) | Estimated Time | Actual Time (hrs)
2024-04-01 | Finalize Q1 Marketing Strategy | John Smith | High | In Progress | 70% | 8 hours | 6.5 hrs
2024-04-02 | Conduct Team Productivity Workshop | Sarah Lee | Medium | Not Started | 0% | 4 hours | -
2024-04-05 | Review Customer Feedback Reports | Mike Chen | High | Completed | 100% | 6 hours | 5.2 hrs
2024-04-08 | Implement Time Tracking Software | Emily Davis | High | In Progress | 40% | 12 hours | 3.8 hrs
2024-04-10 | Optimize Daily Stand-up Meetings | David Wilson | Medium | Not Started | 0% | 3 hours | -