## Worksheet
S.No | Task Description | Assigned To | Target Date | Status | Budget Allocation (USD) | Actual Cost (USD) | Progress %
1 | Conduct market research for new product line | Jane Smith | 2024-05-30 | In Progress | 15,000 | 9,850 | 65%
2 | Optimize supply chain logistics | Michael Chen | 2024-06-15 | Not Started | 30,000 | - | -
3 | Implement time-tracking software | Sarah Williams | 2024-07-10 | Completed | 8,500 | 7,950 | 100%
4 | Train team on productivity tools | David Lee | 2024-06-30 | Scheduled | 5,000 | - | 30%
5 | Review quarterly performance KPIs | Alex Turner | 2024-08-05 | Not Started | 12,000 | - | -