## Worksheet
Date | Task | Assigned To | Priority | Status | Estimated Time (hrs) | Actual Time (hrs) | Progress (%) | Notes
2024-04-01 | Conduct financial workflow audit | Jane Smith | High | In Progress | 8 | 6.5 | 81% | Identify bottlenecks in reporting process.
2024-04-05 | Implement time tracking tool | Mike Johnson | High | Pending Approval | 12 | Awaiting stakeholder sign-off.
2024-04-10 | Review budget allocation for Q2 | Sarah Lee | Moderate | Completed | 4 | 4 | 100%
2024-04-15 | Train team on new productivity dashboard | Team Leads | Medium | Scheduled | 3.5 | 0 | Not Started
Total Tasks: |  |  |  | 4 | Avg. Time per Task: | 6.8 hrs