## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Progress (%) | Status
Project Planning & Scope Definition | 2024-03-01 | 2024-03-15 | 15 | John Smith | 90% | On Track
Market Research & Competitor Analysis | 2024-03-16 | 2024-04-05 | 21 | Sarah Lee | 75% | On Schedule
Product Design & Prototyping | 2024-04-06 | 2024-05-15 | 41 | Mike Chen | 60% | Delayed
Development & Coding Phase | 2024-05-16 | 2024-07-15 | 61 | Alex Rivera | 30% | On Schedule
Testing & Quality Assurance | 2024-07-16 | 2024-08-15 | 31 | Lisa Wong | 0% | Not Started
User Training & Go-Live | 2024-08-16 | 2024-09-30 | 46 | David Kim | 0% | Not Started