## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Define Productivity Goals | 2024-04-01 | 2024-04-05 | 5 | Project Manager | Completed
Conduct Stakeholder Interviews | 2024-04-06 | 2024-04-12 | 7 | Business Analysts | In Progress
Analyze Current Workflows | 2024-04-13 | 2024-04-20 | 8 | Operations Team | Not Started
Propose Productivity Enhancements | 2024-04-21 | 2024-05-03 | 13 | Engineering Team | Planned
Implement and Test Solutions | 2024-05-04 | 2024-05-31 | 28 | IT & DevOps | Not Started
Measure Performance and Adjust | 2024-06-01 | 2024-06-15 | 15 | Project Manager & Team Leads | Not Started