## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Responsible Person
Project Kickoff & Planning | Jan 1, 2024 | Jan 15, 2024 | 15 | 100 | John Smith
Team Training & Onboarding | Jan 16, 2024 | Feb 10, 2024 | 35 | 95 | Sarah Lee
Process Audit & Workflow Review | Feb 11, 2024 | Mar 5, 2024 | 35 | 80 | Mike Chen
Tool Implementation & Integration | Mar 6, 2024 | Apr 15, 2024 | 40 | 75 | Lisa Wong
Performance Monitoring & Optimization | Apr 16, 2024 | Jun 30, 2024 | 75 | 50 | David Kim
Annual Review & Reporting | Jul 1, 2024 | Jul 31, 2024 | 30 | 100 | All Team Members