## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 days | John Smith | On Track
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 days | Sarah Lee | In Progress
Product Design & Prototyping | 2024-04-11 | 2024-05-30 | 60 days | Mike Johnson | Planned
Development & Testing | 2024-06-01 | 2024-08-15 | 95 days | Lisa Chen | Not Started
Launch Preparation | 2024-08-16 | 2024-09-30 | 45 days | David Kim | On Track
Post-Launch Review & Optimization | 2024-10-01 | 2024-11-30 | 60 days | All Team Members | Planned