## Worksheet
Task | Start Date | End Date | Duration | Responsible | Progress (%)
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 day | Project Manager | 100%
Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 days | Business Analysts | 85%
Product Design & Prototyping | 2024-03-26 | 2024-04-15 | 21 days | UX Design Team | 60%
Development Phase (Phase 1) | 2024-04-16 | 2024-05-15 | 30 days | Software Developers | 40%
Testing & Quality Assurance | 2024-05-16 | 2024-06-10 | 35 days | QA Team | 20%
Go-Live & Training | 2024-06-11 | 2024-06-25 | 15 days | Operations Team | 0%