## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible Person
Market Research & Analysis | 2024-04-01 | 2024-04-15 | 15 | On Track | Jane Doe
Product Design & Prototyping | 2024-04-16 | 2024-05-10 | 35 | In Progress | Mike Smith
User Testing & Feedback Collection | 2024-05-11 | 2024-05-31 | 31 | Not Started | Sarah Lee
Development & Coding Phase | 2024-06-01 | 2024-07-15 | 65 | Planned | Alex Chen
Quality Assurance & Bug Fixes | 2024-07-16 | 2024-08-10 | 35 | Not Started | Jordan Patel
Final Review & Stakeholder Approval | 2024-08-11 | 2024-08-25 | 15 | Pending | Team Lead
Productivity Improvement – Gantt Chart (Dashboard View)