## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies | Progress (%) | Milestones
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | John Doe | Completed |  | 100% | Planning Finalized
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 25 | Jane Smith | In Progress | Project Initiation | 60%
Product Design & Prototyping | 2024-04-11 | 2024-05-30 | 50 | Mike Johnson | Not Started | Market Research Finalized | 0%
Development & Coding | 2024-06-01 | 2024-08-31 | 90 | Sarah Lee | Not Started | Product Design Approved | 0%
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 45 | David Brown | Not Started | Development Complete | 0%
Deployment & Launch | 2024-10-16 | 2024-10-31 | 16 | Emma Taylor | Not Started | Testing Complete & Sign-off | 0% | Product Launch Successful
Post-Launch Review & Feedback Collection | 2024-11-01 | 2024-11-30 | 30 | Team Lead (All) | Not Started | Launch Completed | 0%