## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Progress (%)
Define Productivity Goals | 2024-03-01 | 2024-03-05 | 5 | John Smith | Completed | 100%
Conduct Employee Productivity Audit | 2024-03-06 | 2024-03-15 | 10 | Sarah Lee | In Progress | 65%
Implement Time Tracking System | 2024-03-16 | 2024-04-10 | 25 | Mike Chen | Not Started | 0%
Train Staff on New Tools | 2024-04-11 | 2024-04-25 | 15 | Lisa Wong | Not Started | 0%
Review Monthly Productivity Reports | 2024-05-01 | 2024-05-31 | 30 | John Smith | Not Started | 0%
Optimize Work Processes | 2024-06-01 | 2024-07-15 | 45 | Sarah Lee & Mike Chen | Not Started | 0%